## Task Sheet
Lemongrabs Robot Tasks for Assignment 3
# | Task | Extra details | do Before | do After | assigned To | status | link to code/pseudo code
1 | Create new driveStraight and driveAngle functions | 1) Similar to assignment 2, but functions that accept distance and angle variables | everything | - | Paul | Done | Task 1 code
2 | Create scan360 function for use in start position or when robot is recovering from dead-ends, cliffs, virtual walls | 1) Initial Scan 360 degrees to find all walls and where there is space to move. Robot should orientate to direction of open space (no walls). | everything | - | Paul | Done
2) The 360 scan should store distances every 50 half-steps (45 degrees) in the local_map array.
3) Do the above with just 1 open space (place robot in a 'dead-end')
NOTE: After the above is complete. This function will be later improved with taking input from the global_map array, to allow the robot to choose which open space to traverse when there is more than 1 open spaces
NOTE2: Do not worry about the triggering this from dead-ends, cliffs, virtual walls for now"
3 | Create scan180 function | 1) Similar to task 2, but just fill the front 180 degrees of distance information into the local_map array | task 4 | task 2 | Paul | Done
4 | Create global_map array and explore function. Integration of tasks 1-3 | 1) This task is to integrate tasks 1-3, allowing the robot to travel around the map in a simple fashion, without bump/cliff/victim/etc sensors, and without any course corrections Includes code for the global_map array and search/return to home algorithm. | - | tasks 1-3 | Paul | In progress
2) Includes code for the global_map array and search/return to home algorithm.
3) Algorithm used is either going to be Paul's method or some other method. Still to decide
5 | Create 3 songs | 1) Compose 3 songs to play for the start/end, 1st victim, and 2nd victim. | - | - |  | Not started
2) Songs should be written to eeprom (since they take a lot of memory.
3) Songs should be read from eeprom and sent to robot during setup (I think, need to check data sheet)
6 | Add in virtual wall sensor | 1) Create virtual wall sensor and test it. | - | - | Nick | In progress
7 | Add in bump/cliff/virtual wall sensor and recovery | 1) Create a way for robot to recover when bump/virtual wall or cliff sensors are triggered | - | task 6. task 4 | Nick | Not started
2) Prefer to create this for it to work in exploring mode
3) Would involve updating the local_map_array to exclude the cliff path, and prob temp update on global_map
8 | Add in victim sensor | 1) Create victim sensor and test it. Do not need to worry about finding a 2nd victim or any of that crap | - | task 4, 5 |  | Not started
9 | Obstacle avoidance, recalibrating position | 1) Using the local_map array, robot should know where in the current 1x1 node it is. | - | task 4 |  | Not started
2) When robot is in a dead-end node (3 walls), robot should use opportunity to plan a perfect travel angle/distance to the previous node
3) When robot is surrounded by 2 walls, robot should course correct to the next node, using information for from current angle/distance from current node
Note: Will involve pythagoras and maybe sin/cos stuff
Note2: This is probably going to be a pain in the ass, but would be awesome if it works
9 | Play song when victim sensor triggered | 1) Play song when first victim is found. Set a flag to not play song again in current node | - | task 8 |  | Not started
2) Second song should play when a victim is found that is not in the first victim node (involves global_map array)
10 | Test all the above shit works together | 1) Make tweaks if needed. Should be sweet….. | - | tasks 1-9 |  | Not started
11 | Add in return to start position | 1) Using the global_map robot should return to start position from the current position via the shortest route | - | everything else |  | Not started

## Code or Pseudo Code
Task # | Code
1 | int driveStraight(int distance) { int distance_traveled = 0; DRIVE_STRAIGHT(); while (distance_traveled < distance) { distance_traveled += distanceAngleSensor(DISTANCE); } DRIVE_STOP(); return distance_traveled; } int driveAngle(int angle) { int angle_turned = 0; if (angle > 0) SPIN_LEFT(); if (angle < 0) SPIN_RIGHT(); while(angle_turned < angle) { angle_turned += distanceAngleSensor(ANGLE); } DRIVE_STOP(); return angle_turned; }

## Astar
Initial scan |  |  |  | Step 2 |  |  |  | Step 5 |  |  |  |  | Step 8 |  |  |  |  | Step 11 |  |  |  |  | Step 14
4 | R | 2 | G | 255 | 255 | 2 | G | 255 | 255 | R | G |  | 255 | 255 | 254 | G | 2 | 255 | 255 | 254 | G | 2 | 255 | 255 | 254 | G | 2
| 4 |  |  | R | 4 | 3 | 2 | 255 | 255 | 3 | 2 |  | 255 | 255 | 255 | 253 | 3 | 255 | 255 | 255 | 255 | 3 | 255 | 255 | 255 | 2 | 3
|  |  |  | 6 | 5 | 4 | [7 empty] | 255 | R | 255 | 4 |  |  | 255 | R | 255 |  |  | 255 | 254 | R
[15 empty] | 7 | 6 | 5 |  |  |  | 6 | 5 |  |  | 255 | 255 | 255
After local input |  |  |  | Step 3 |  |  |  | Step 6 |  |  |  |  | Step 9 |  |  |  |  | Step 12 |  |  |  |  | Step 15
6 | R | 255 | G | 255 | 255 | 3 | G | 255 | 255 | 254 | G |  | 255 | 255 | 254 | G | 2 | 255 | 255 | 254 | G | 2 |  |  |  | G | 2
5 | 255 | 3 | 2 | 255 | R | 4 | 3 | 255 | 255 | R | 2 |  | 255 | 255 | 255 | 253 | 3 | 255 | 255 | 255 | 253 | 3 |  |  |  | 2 | R
[5 empty] | 5 | 4 | [8 empty] | 255 | 5 | 4 |  |  | 255 | 254 | 4 |  |  |  |  | 255
[14 empty] | 8 | R | 6 | 5 |  |  | 255 | R | 5
Step 1 |  |  |  | Step 4 |  |  |  | Step 7 |  |  |  |  | Step 10 |  |  |  |  | Step 13 |  |  |  |  | Step 16
R | 255 | 2 | G | 255 | 255 | 2 | G | 255 | 255 | 254 | G | 2 | 255 | 255 | 254 | G | 2 | 255 | 255 | 254 | G | 2 |  |  |  | G | 2
5 | 4 | 3 | 2 | 255 | 255 | R | 2 | 255 | 255 | R | 253 | 3 | 255 | 255 | 255 | 253 | 3 | 255 | 255 | 255 | 3 | 3 |  |  |  | R | 3
[6 empty] | 4 | 3 |  |  | 6 | 5 | 4 |  |  | 255 | 5 | 4 |  |  | 255 | 254 | 4
[15 empty] | 255 | R | 5 |  |  | 255 | 255 | R